Construction Procurement North Wales (CPNW): Update Paper May 2013

- Next steps/ latest update

  - Tender documents have been drafted and are currently being reviewed by legal advisors, framework management structure has been developed.

  - Engagement Strategy has been set see below:

  - Officers review workshop- May

  - Community benefits briefing session for Contractors/ Proactis training (Engagement will include all targeted training and recruitment agencies (Job Centre Plus, New Work Connections, Careers Wales, CITB, Business Wales etc) to ensure they are in the best possible position to help and support suppliers as well as agree protocol) Invitations to be issued via PIN and CITB- June

  - Assembly Members briefing- June

  - Federations briefing- June

  - Expected date for publication of the OJEU Notice mid June 2013. See updated milestones below.

- Introduction

The CPNW project is set up as a collaborative project between the 6 North Wales authorities led by Flintshire and Denbighshire County Councils.

AIM: To provide a simple, easy to use and transparent process to manage and deliver the schools construction programmes collaboratively in North Wales.

OBJECTIVE: To create a new bespoke procurement vehicle by Autumn 2013, tendered via the OJEU process, which allows the participating local authorities (and other public sector organisations as appropriate) to instruct construction activities. To provide a lean and efficient process that is cost effective and delivers a project (building) that is fit for purpose.

- Current progress

Following a procurement options paper in September 2012 to the North Wales Local Authorities Chief Executive Officers, it was agreed that  following Welsh Governments clarification that a framework approach is favoured and required to access the 21st Century Schools Programme funding, the CEO’s supported the officer recommendation to progress to the next stage in the process; which was to seek consultation of key stakeholders on the proposal to develop a high value framework (over £4.35m) and develop a regional standardised approach to procure projects below this level.

Currently the project is in the latter stages of the consultation stage, the project has engaged the construction industry and key stakeholder to ensure that the evolving Procurement Strategy covers all the key areas and that feedback from the industry is incorporated into the document. This has been a very positive experience proven by the feedback from the industry.

  - Engagement

An OJEU PIN (Prior Information Notice) was issued to the construction industry in October 2012 with a link to a questionnaire (setting out 13 questions covering key proposal areas such as lotting strategy, types of contracts and community benefits). Seventy two responses were received.

A follow up Contractor briefing event was then held on 12th November 2012 with over 100 Contracting representatives attending. The questionnaire results as well as the driver and scope of the project were presented at the event.

The project team has also engaged with Value Wales, Constructing Excellence Wales, Construction Skills Wales and Menter a Busnes. These relationships are essential and key to the successful implementation of the project.

  - Reporting

Along with the construction industry dialogue the project team have also reported and updated several key stakeholder groups to ensure clear communication and endorsement and feedback including:

- North Wales Chief Executive Officers Forum

- North Wales Leadership Board

- North Wales Economic Ambitions Board

- North Wales Economic Forum

- Procurement Strategy - What is it?

This document is an operational document used to provide a structure for implementation (setting up the framework) and ensure that Cabinets of the 6 North Wales authorities are fully informed.

How has the engagement and questionnaire with the construction industry been used?

The Construction industry (questionnaire and event feedback) as well as engagement with key stakeholders has helped inform the Procurement Strategy document, the key points:

  - Lotting structure for the framework

| Indicative Value Bands | No. of Projects | Value £m | No of Contractors |
| --- | --- | --- | --- |
| £4.35m > £7.5m | 6 no. | £32m | 6 no. |
| £7.5m > £15m | 7 no. | £84m | 6no. |
| £15+ | 2no. | £60m | 3no. |
| TOTAL | 15 no. | £176m |  |

The above indicative lots are envisaged as being appropriate to the users’ needs and are subject to approval/endorsement by the 6 Local Authorities Cabinets. The Programme of projects is also subject to change and each project will need to be approved by Welsh Government.

  - Community benefits and economic, social and environmental impact are a key element to the Procurement strategy

  - The project and strategy is committed to simplify the procurement process, maintaining a positive and active engagement with industry and working closely with key stakeholders such as Value Wales to ensure that we fully comply with the Welsh Government Procurement Policy Statement.

- Key Project Milestones

| Process | Date |
| --- | --- |
| Develop the Procurement options paper and report to the CEO NW Forum- Discussion of approaches and consideration of officer recommendations | 13th September 2012 |
| Issue Prior Information Notice via OJEU to the industry with Questionnaire | 19th October 2012 |
| Consultation with the Construction industry engagement event Discussion with the NW Regional Leadership Board | 12th November 2012 9th November 2012 |
| Develop the Procurement Plan for preferred approach | October- November 2012 |
| Consultation/ Briefing with 6 authorities relevant Cabinet members Update the North Wales Ambitions Board Update ADEW | November 2012 14th November 2012 |
| Take the Procurement Plan to the CEO NW Forum for approval/support for the project to proceed for democratic consideration by Cabinets | 30th November 2012 |
| North Wales Economic Forum | 6th December 2012 |
| Take Procurement Plan to respective Cabinets for democratic consideration/approval | December 2012-February 2013 |
| Prepare Tender documentation | December 2012-June2013 |
| Publish the OJEU Notice | June 2013 |
| ITT responses | June-July 2013 |
| Evaluation | August- September 2013 |
| Select Contractors | September 2013 |
| Publish OJEU Award Notice | Oct 2013 |

* there is a time slippage in the publishing of the OJEU Notice to allow more time to develop the documentation for an open procedure and engagement with relevant stakeholders before publication of the OJEU Notice.

- Glossary

| Term | Definition |
| --- | --- |
| CEO NW Forum | Chief Executive Officer North Wales Forum: Group convened by Welsh Local Government Association, forum meeting of the 6 North Wales authorities Chief Executives. |
| OJEU Process | OJEU - the Official Journal of the European Union. This is the publication in which all tenders from the public sector which are valued above a certain financial threshold according to EU legislation must be published. |
| ADEW | The Association of Directors of Education in Wales (ADEW) is the professional group of local authority officers accountable for statutory education functions in each of the Local Authorities in Wales. |
| Regional North Wales Economic Ambitions Board | A new regional body to offer clear guidance to develop the North Wales economy. Vehicle for closer collaboration in economic development across all of the North Wales’s 6 local authorities. |
| North Wales Regional Leadership Board | The North Wales Regional Leadership Board (NWLPB) is made up of the Leaders and Chief Executives of the six North Wales Councils plus the lay and executive leaders of the other key public service bodies in the region: Conwy County Borough Council Denbighshire County Council Gwynedd Council Isle of Anglesey County Council Flintshire County Council Wrexham County Borough Council The Chair and Chief Executive of the Betsi Cadwaladr University Health Board, The Chair and Chief Executive of the North Wales Police Authority, The Chief Constable of the North Wales Police and The Chair and Chief Fire Officer of the North Wales Fire and Rescue Authority. |
| North Wales Economic Forum (NWEF) | The NWEF is a forum set up to bring the private and public sector to discuss business and works with local authorities. Membership includes: Federation of Small Businesses, CBI (Confederation British Industry) Cymru, Institute of Directors, Wales Cooperative, TAITH, and Wales Council for Voluntary |